## Sheet1
Subcontractor: | Balaji Construction
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS (1%) | SD (5%) | On Commissioning | Hydro Testing | GST_SD_Amount | Hold Amount For Material | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% |  |  | 18% | [5 empty] | 1%
57752
57752 | Khokani Village Pipeline Work | 2023-07-07 | 1 | 218144 | 0 | 218144 | 39266 | 257410 | 2181.44 | 10907.2 | 10907.2 | 21814.4 | 39266 | 0 | 172334 |  | RIUP23/1062 | 150000 | 1500 | 148500 | 12-07-2023 NEFT/AXISP00406496251/RIUP23/1062/BALAJI CONSTRUC ₹ 1,48,500.00
57752 | Khokani Village Pipeline Work | 2023-11-06 | 8 | 225997 | 7600 | 218397 | 39311.46 | 257708.46 | 2183.97 | 10919.85 | 21839.7 | 21839.7 | 39311.46 | 15666 | 145947.78 |  | RIUP23/1097 | 23835 | 0 | 23835 | 21-07-2023 NEFT/AXISP00408446742/RIUP23/1097/BALAJI CONSTRUC 23835.00
57752 | Khokani Village Pipeline Work | 2024-01-13 | 10 | 432896 | 0 | 432896 | 77921.28 | 510817.28 | 4328.96 | 21644.8 | 43289.6 | 43289.6 | 77921.28 | 0 | 320343.04 |  | RIUP23/3474 | 100000 | 1000 | 99000 | 10-11-2023 NEFT/AXISP00443237220/RIUP23/3218/BALAJI CONSTRUCTIO/UBIN0572632 99000.00
57752 | GST Release Note |  | 1 & 8 | 78577.46 | [10 empty] | 78577.46 |  | RIUP23/3474 | 46947 | 0 | 46947 | 01-12-2023 NEFT/AXISP00448665328/RIUP23/3474/BALAJI CONSTRUCTIO/UBIN0572632 ₹ 46,947.00
57752 | GST Release Note |  | 10 | 77921.28 | [10 empty] | 77921.28 |  | RIUP23/4419 | 320342 | 0 | 320342 | 25-01-2024 NEFT/AXISP00464876202/RIUP23/4419/BALAJI CONSTRUCTIO/UBIN0572632 320342.00
57752 | [19 empty] | 78577 | 30-03-2024 NEFT/AXISP00486493289/RIUP23/4841/BALAJI CONSTRUCTIO/UBIN0572632 78577.00
57752 | [19 empty] | 77921 | 30-01-2025 NEFT/AXISP00606020248/RIUP24/2211/BALAJI CONSTRUCTIO/UBIN0572632 77921.00
[16 empty] | 57938 |  | 0 | 0
57938 | Khokani Village Pump house Work | 2023-07-07 | 2 | 105000 | 56170 | 48830 | 8789 | 57619 | 488.3 | 4883 |  |  | 8789 | 0 | 43459 |  | RIUP23/1072 | 43459 | 0 | 43459 | 14-07-2023 NEFT/AXISP00406995905/RIUP23/1072/BALAJI CONSTRUC 43459.00
57938 | Khokani Village Pump house Work | 2023-09-26 | 6 | 210000 | 0 | 210000 | 37800 | 247800 | 2100 | 21000 |  |  | 37800 | _ | 186900 |  | RIUP23/2421 | 186900 | 0 | 186900 | 17-10-2023 NEFT/AXISP00435088305/RIUP23/2421/BALAJI CONSTRUCTIO/UBIN0572632 186900.00
57938 | GST Release Note |  | 2 | 8789 | [10 empty] | 8789 |  |  |  |  | 8789 | 06-03-2024 NEFT/AXISP00477945203/RIUP23/4842/BALAJI CONSTRUCTIO/UBIN0572632 8789.00
57938 | GST Release Note |  | 6 | 37800 | [10 empty] | 37800
58241
58241 | Khokani Village Boundary wall Work | 2023-07-07 | 3 | 144900 | 0 | 144900 | 26082 | 170982 | 1449 | 7245 |  |  | 26082 |  | 136206 |  | RIUP23/1094 | 136206 | 0 | 136206 | 15-07-2023 NEFT/AXISP00407289885/RIUP23/1094/BALAJI CONSTRUC ₹ 1,36,206.00
58241 | Khokani Village Boundary wall Work | 2023-09-26 | 5 | 139300 | 0 | 139300 | 25074 | 164374 | 1393 | 6965 |  |  | 25074 |  | 130942 |  | RIUP23/2422 | 130942 | 0 | 130942 | 17-10-2023 NEFT/AXISP00435088306/RIUP23/2422/BALAJI CONSTRUCTIO/UBIN0572632 130942.00
58241 | GST Release Note |  | 3 & 5 | 51156 | [10 empty] | 51156 |  |  |  |  | 51156 | 30-03-2024 NEFT/AXISP00486493282/RIUP23/4839/BALAJI CONSTRUCTIO/UBIN0572632 51156.00
58486
58486 | Randawali , Jhabarpur,Harinagar Village Pipeline Work | 2023-08-10 | 4 | 470584 | 0 | 470584 | 84705 | 555289 | 4705.84 | 23529.2 | 23529.2 | 47058.4 | 84705 | 1180 | 370581 |  | RIUP23/1497 | 370582 | 0 | 370582 | 14-08-2023 NEFT/AXISP00415803578/RIUP23/1497/BALAJI CONSTRUC ₹ 3,70,582.00
58486 | Randawali , Jhabarpur,Harinagar Village Pipeline Work | 2023-10-14 | 7 | 691770.5 | 4560 | 687211 | 123698 | 810909 | 6872.11 | 34360.55 | 34360.55 | 68721.1 | 123698 | 23007 | 519890 |  | RIUP23/2845 | 51988 | 0 | 519888 | 26-10-2023 NEFT/AXISP00437006020/RIUP23/2845/BALAJI CONSTRUCTIO/UBIN0572632 519888.00
58486 | Randawali , Jhabarpur,Harinagar Village Pipeline Work | 2024-02-13 | 11 | 1592282 | 0 | 1592282 | 286611 | 1878893 | 15922.82 | 79614.1 | 159228.2 | 159228.2 | 286611 | 114693 | 1063596 |  | RIUP23/3991 | 200000 | 2000 | 198000 | 27-12-2023 NEFT/AXISP00455794960/RIUP23/3991/BALAJI CONSTRUCTIO/UBIN0572632 ₹ 1,98,000.00
58486 | GST Release Note |  | 4 & 7 | 208403 | [10 empty] | 208403 |  | RIUP23/3991 | 20843 | 208.43 | 208403 | 28-02-2024 NEFT/AXISP00474588154/RIUP23/4840/BALAJI CONSTRUCTIO/UBIN0572632 208403.00
58486 | Randawali , Jhabarpur,Harinagar Village Pipeline Work | 2024-06-11 | 1 | 924297 | 0 | 924297 | 166373 | 1090670 | 9242.97 | 46214.85 | 92429.7 | 92429.7 | 166373 | 4184 | 679796 |  |  |  |  | 500000 | 12-03-2024 NEFT/AXISP00480051200/RIUP23/4787/BALAJI CONSTRUCTIO/UBIN0572632 500000.00
58486 | GST Release Note |  | 1 | 166373 | [10 empty] | 166373 |  |  |  |  | 365596 | 24-04-2024 NEFT/AXISP00493457035/RIUP24/0271/BALAJI CONSTRUCTIO/UBIN0572632 365596.00
58486 | GST Release Note |  | 11 | 286611 | [10 empty] | 286611 |  |  |  |  | 500000 | 16-07-2024 NEFT/AXISP00519021668/RIUP24/0953/BALAJI CONSTRUCTIO/UBIN0572632 500000.00
58486 | Randawali , Jhabarpur,Harinagar Village Pipeline Work | 2024-10-28 | 2 | 587193 | 52500 | 534693 | 96245 | 630938 | 5346.93 | 26734.65 | 26734.65 | 53469.3 | 96245 |  | 422407 |  |  |  |  | 179795 | 03-08-2024 NEFT/AXISP00524511286/RIUP24/1356/BALAJI CONSTRUCTIO/UBIN0572632 179795.00
58486 | GST Release Note |  | 2 | 96245 | [10 empty] | 96245 |  |  |  |  | 286611 | 18-10-2024 NEFT/AXISP00555372145/RIUP24/2212/BALAJI CONSTRUCTIO/UBIN0572632 286611.00
58486 | [19 empty] | 300000 | 26-12-2024 Debit N/RIUP24/2402/BALAJI CONSTRU/INDBN26123786894 300000.0
58486 | [19 empty] | 262618 | 28-03-2025 NEFT/AXISP00641455072/RIUP24/3451/BALAJI CONSTRUCTIO/UBIN0572632 262618.00
59087
59087 | Ahrora Village PIPELINE DISTRIBUTION NETWORK Work | 2023-12-18 | 9 | 624115 | 4920 | 619195 | 111455 | 730650 | 6191.95 | 30959.75 | 61919.5 | 61919.5 | 111455 | 7507 | 450697 |  | RIUP23/1818 | 150000 | 1500 | 148500 | 01-09-2023 NEFT/AXISP00420941794/RIUP23/1818/BALAJI CONSTRUCTIO/UBIN0572632 ₹ 1,48,500.00
59087 | GST Release Note |  | 9 | 111455 | [10 empty] | 111455 |  | RIUP23/4009 | 302196 | 0 | 302196 | 09-01-2024 NEFT/AXISP00460826663/RIUP23/4009/BALAJI CONSTRUCTIO/UBIN0572632 302196.00
59087 | [19 empty] | 111455 | 30-03-2024 NEFT/AXISP00486493283/RIUP23/4838/BALAJI CONSTRUCTIO/UBIN0572632 111455.00